## Test plan
1. Test Plan Information
Field | Details
Test Plan ID | TP-001
Project Name | SauceDemo E-Commerce Website
Application Under Test | SauceDemo
Testing Type | Manual Testing
Testing Level | System Testing
Prepared By | Abdul Basit
Version | 1
Status | Draft
Test Environment | Windows 10/11, Google Chrome
Test URL | https://www.saucedemo.com/?utm_source=chatgpt.com
2.Introduction
The purpose of this Test Plan is to define the testing approach, scope, objectives, resources, test environment, and deliverables for testing the SauceDemo e-commerce website.
The testing will focus on verifying that the major functionalities of the application work according to the expected behavior and identifying defects that may affect the application's functionality, usability, or user experience.
3. Testing Objectives
The main objectives are:
Verify user login functionality.
Verify product listing and product details.
Verify product sorting.
Verify Add to Cart functionality.
Verify Remove from Cart functionality.
Verify cart functionality.
Verify checkout functionality.
Verify order completion.
Verify logout functionality.
Identify and document defects.
Verify that reported defects are fixed through retesting.
4. Scope of Testing
The following modules will be tested:
Login
↓
Products
↓
Product Details
↓
Shopping Cart
↓
Checkout
↓
Order Confirmation
↓
Logout
5. Out of Scope
The following areas will not be tested in this manual testing project:
Backend/source code testing
Server-side testing
Database testing
Load testing
Stress testing
Security penetration testing
Real payment gateway testing
Production infrastructure testing
6. Testing Approach
Testing techniques will include:
Positive Testing
Negative Testing
Boundary Value Analysis
Equivalence Partitioning
Exploratory Testing
Retesting
Regression Testing
Smoke Testing
Sanity Testing
UI Testing
Compatibility Testing
7. Test Types
Test Type | Purpose
Functional Testing | Verify application functionality
UI Testing | Verify UI elements and layout
Smoke Testing | Verify major functionality is working
Sanity Testing | Verify specific changes/fixes
Regression Testing | Ensure existing functionality still works
Retesting | Verify reported defects after fixes
Compatibility Testing | Check behavior across supported browsers
8. Test Environment
Example:
Item | Configuration
OS | Windows 10/11
Browser | Google Chrome
Browser Version | Latest available during testing
Testing Type | Manual
Internet | Required
Application | SauceDemo
9. Test Data
Use the test credentials provided by SauceDemo.
Example:
Data | Value
Valid Username | standard_user
Valid Password | secret_sauce
Invalid Username | invalid_user
Invalid Password | invalid_password
First Name | Abdul
Last Name | Basit
Postal Code | 54000
10. Entry Criteria
Testing can start when:
Website is accessible.
Application is available for testing.
Test environment is ready.
Test data is available.
Test scenarios and test cases have been prepared.
11. Exit Criteria
Testing can be considered complete when:
All planned test cases have been executed.
Pass/Fail results have been recorded.
Critical defects have been reported.
Failed test cases have been investigated.
Retesting has been completed where applicable.
Test execution report has been prepared.

## Tset Scanerio
SauceDemo — Test Scenarios
Scenario ID | Module | Test Scenario
TS-001 | Login | Verify that the user can log in with valid credentials
TS-002 | Login | Verify that the user cannot log in with an invalid username
TS-003 | Login | Verify that the user cannot log in with an invalid password
TS-004 | Login | Verify validation when username is empty
TS-005 | Login | Verify validation when password is empty
TS-006 | Login | Verify validation when both username and password are empty
TS-007 | Login | Verify login behavior for locked-out user
TS-008 | Login | Verify that the password field masks the entered password
TS-009 | Login | Verify that the user can log out successfully
TS-010 | Products | Verify that the Products page is displayed after successful login
TS-011 | Products | Verify that products are displayed correctly
TS-012 | Products | Verify that each product has a name
TS-013 | Products | Verify that each product has a price
TS-014 | Products | Verify that each product has an image
TS-015 | Products | Verify that each product has an Add to Cart button
TS-016 | Products | Verify product sorting by name A-Z
TS-017 | Products | Verify product sorting by name Z-A
TS-018 | Products | Verify product sorting by price low-to-high
TS-019 | Products | Verify product sorting by price high-to-low
TS-020 | Product Details | Verify that the user can open a product details page
TS-021 | Product Details | Verify product name on the details page
TS-022 | Product Details | Verify product description on the details page
TS-023 | Product Details | Verify product price on the details page
TS-024 | Product Details | Verify product image on the details page
TS-025 | Product Details | Verify Add to Cart functionality from product details
TS-026 | Product Details | Verify Back to Products functionality
TS-027 | Cart | Verify that a product can be added to the cart
TS-028 | Cart | Verify that multiple products can be added to the cart
TS-029 | Cart | Verify that the cart count updates after adding a product
TS-030 | Cart | Verify that the selected product appears in the cart
TS-031 | Cart | Verify that a product can be removed from the cart
TS-032 | Cart | Verify that the cart count updates after removing a product
TS-033 | Cart | Verify that multiple products can be removed
TS-034 | Cart | Verify that the cart displays the correct product name
TS-035 | Cart | Verify that the cart displays the correct price
TS-036 | Cart | Verify Continue Shopping functionality
TS-037 | Checkout | Verify that the user can proceed to checkout
TS-038 | Checkout | Verify validation for empty First Name
TS-039 | Checkout | Verify validation for empty Last Name
TS-040 | Checkout | Verify validation for empty Postal Code
TS-041 | Checkout | Verify checkout with valid customer information
TS-042 | Checkout | Verify that the checkout overview displays selected products
TS-043 | Checkout | Verify product prices on the checkout overview
TS-044 | Checkout | Verify total amount calculation
TS-045 | Checkout | Verify Cancel functionality on checkout
TS-046 | Order | Verify that the user can complete an order
TS-047 | Order | Verify successful order confirmation message
TS-048 | Order | Verify that the user can return to the Products page after completing an order
TS-049 | Navigation | Verify navigation between Products, Cart, and Checkout pages
TS-050 | UI | Verify that buttons, links, labels, images, and page elements are displayed correctly